## Sheet1
IS MILESTONE | TASK DETAIL | DESCRIPTION | SERVICE | MAN DAYS
yes | System Design | System Design
no | Requirement Analysis and Process Flow | The project Requirement Analysis along with the process flow for the information flow between various screens. | System Design | 2
no | DB Design Updates | Creating DB Schema | System Design | 3
yes | Design Phase | Design Phase
no | Backend:- Initial Code Setup | Creating Backend Setup With Admin Panel Configration | System Design | 2
no | App Prorotyping | App Prorotyping | UI/UX Design | 2
no | App design | App design | UI/UX Design | 2
yes | Admin | Admin Panel
yes | Web Services | Web Services
yes | Users Customers Sitemap (Mobile) | Users Customers Sitemap (Mobile)
no | Splash | Splash screen (2-3 seconds) and app icons | Software Development | 1
no | Login | Login - UI design, validation and functionality | Software Development | 2
no | Sign up | Login - UI design, validation and functionality | Software Development | 2.25
no | Login with Social Media | Login with Social Media (Twitter, Facebook, Instagram) - Integration Social SDK | Software Development | 2.5
no | Forgot Password | Forgot Password - UI design and functionality | Software Development | 1.5
no | Home (Search) | Home - UI design and functionality ➢ Search functionality | Software Development | 1.5
no | Home (Filters) | ➢ Filters o Category & Sub-Category o Price Range o Color Preference | Software Development | 2.5
no | Home (List of products) | ➢ List of Products o Product Image (Multiple) o Product Name o Offers (if Any) o Short Description o Long Description o Select / Enter Delivery Address o In Stock / Not o Select Color (if choices available) o Select Size (if Size Available) o View Provided Ratings & Reviews | Software Development | 2.75
no | Home (Action) | ➢ Action o Buy Now * Select Added Payment Card * Add New Card (If no card is added) * Enter Coupon Code (if any) o Add to Cart o Mark as Favorite | Software Development | 3.5
no | Add to Cart | Add to Cart ➢ View Added Product Details - UI design and functionality o Set Quantity o Proceed to Pay o Select Delivery Address or Add New Address | Software Development | 2.5
no | My Favorites | My Favorites ➢ List of Added Products - UI design and functionality ➢ Action o View More Details o Remove from List | Software Development | 2.75
no | My Orders | My Orders - UI design and functionality ➢ List of Orders o View Order Details o View Order Status * Pending * Received * Dispatched * On the Way * Delivered * Cancelled ➢ Action o Buy it Again o Write a Review o Cancel Your Order o Refund Your Order o Filter by Order * All * Open Orders * Cancelled Orders o Filter by Time * Last 30 Days * Last 6 Months * Year Wise | Software Development | 6.75
no | Notifications | Notifications ➢ List of Notifications o Offer Related o Coupon Related o Order Related o Payment Related | Software Development | 2.25
no | Settings | Settings - UI design and fuctionality ➢ My Profile o Edit / Update ➢ Change Password ➢ Customer Support o Chat with Customer Care | Software Development | 5.5
no | Sign Out | Sign Out | Software Development | 1.5
yes | General functionality | General functionality
no | Push Notifications API Integration (FCM and APN) | Push Notifications API Integration (FCM and APN) | Software Development | 3
no | Social Media - Twitter Integration | Social Media - Twitter Integration | Software Development | 1.5
no | Social Media - Facebook Integration | Social Media - Facebook Integration | Software Development | 1.75
no | Social Media - Instagram Integration | Social Media - Instagram Integration | Software Development | 2
no | Payment gateway Integration | Payment gateway Integration | Software Development | 2.5
no | Firebase Cloud Messaging (Push Notification) | Firebase Cloud Messaging (Push Notification) | Software Development | 2
yes | QA & Testing | QA & Testing
no | Testing of the System | Testing of the System | QA & Testing | 6
yes | System Integration and deployment | System Integration and deployment
no | UAT Revisions with Client | UAT review | Software Development | 6
no | Uploading app to play store | Uploading app to play store | Software Development | 1
no | Uploading app on app store | Uploading app on app store | Software Development | 1
no | Deployment of admin portal on live server | Deployment of admin portal on live server | Software Development | 1